Sponsored Projects Close-Out Checklist

90 Days Prior To Award End Date Through Close Date

## ACTION ITEMS

Verify if award will be closed or extended. If award is being extended - Submit a no cost extension request to OVPR. (NCE Process overview: https://research.gwu.edu/award-adjustments#NCE )

Inform research staff/students that award is ending - Work with the HR Client Partner on terminating staff - Or move staff to other funding source

Verify effort processed and posted correctly. - If necessary, submit Labor Redistributions for previous pay periods - Submit EPAFs for period beyond the award end date for all staff being charged to the awards

Verify that all expenditures are processed and posted. If necessary, - Submit Departmental Corrections Forms (DCF) and CTJF to transfer expenditures on or off the award - Submit invoices for open Purchase Orders to clear encumbrances - Liquidate all outstanding encumbrances - Request, review sign and submit final invoices from consultants/contractors - Ensure that all Tuition expenditures posted correctly - Ensure that all Stipend expenditures posted correctly - Submit PCard & Travel expenses in Concur - Identify and submit any outstanding requests

Verify that Subaward(s) is/are ready for closeout. - Deliverables/milestone have been met - Final sub award invoices and effort certification have been received and have been submitted for payment (invoices should be marked final) - Review all sub expenditures and ensure that they are all posted to the correct subaward #. If not, request that the expenditures be transferred to correct sub award # by submitting DCFs.

Verify cost share commitment has been met - Review cost share expenditure and verify if all applicable costs h posted - If reason for unmet cost share is justifiable, submit cost share adjustment request to the sponsor (this should be done no later than 90 days before the award end date) - If all expenditures have posted and if the sponsor does not approve an adjustment, transfer expenses from main award to cost share award to make the spending level equal

Review and submit all final reports - Final Technical Report - Patent and Property Report - Final invention Statement - Disposition of fixed assets - Other (review your award document for any additional reporting)

Other Close out Tasks to be completed - Account for any real and personal property - Review and ensure all expenditures posted to the appropriate expenditure account codes - Review award for administrative costs that were not budgeted and do not have prior approval. Submit DCFs/CTJF if necessary - Ensure Suspense and Failed Funds has cleared - If fixed price award, submit residual funds transfer request to GCAS - Coordinate with GCAS SPFA the final close out of the award. Inform SPFA of any outstanding credits

Reminders: Please remember that expenditure discrepancies, if any, must be identified thirty days prior to the closing award date to be reflected on the final financial report. Additional costs may not be posted after the final report draft. Notification of the completed technical/progress report will need to be provided to OVPR.

Resources: OVPR Handbook, Close-Out (page 42) Award Management and Close-out Policy https://research.gwu.edu/award-management